## Sheet1
Bug ID | Bug Title | Status
Bug-001 | Failed to Fetch Error on Admin Panel After User Conversion | Open
Bug-002 | Duplicate Entry Error on Admin Panel After User Conversion | Open
Bug-003 | Incorrect Amount Sign Alignment in Arabic | Open
Bug-004 | In Market Index, the graph alignment becomes incorrect after changing the application language. | Open
Bug-005 | Language: | Open
Bug-006 | Blocked User Screen Opens Twice | Open
Bug-007 | Internet Connection Issue (TRC20, marketplace, kyc, about founder, cart) | Open
Bug-008 | In the mobile app, notifications are grouped date-wise, for example 8 September, 9 September. However, on the web, notifications are grouped week-wise/month-wise, such as Last Week and Last Month | Open
Bug-009 | The drawer menu in the Admin, Partner, and User panels should extend fully to the bottom of the screen. | Open
Bug-010 | The FAQs need to be updated | Open
Bug-011 | Service Pack validations are not working correctly --- Admin | Open
Bug-012 | When placing an order using Pay with RBF from Delivery Schedule, the order is successfully placed and a success popup is displayed. After closing the popup using the cross button, the user is not navigated to the Marketplace. | Open
Bug-013 | When an order is placed from the Product Details screen or Marketplace using Pay with Card, the order is successfully placed and a success popup is displayed. After closing the popup using the cross button, the relevant screen does not refresh to reflect | Open
Bug-014 | The Market Index graph on the Web is not synchronized with the Mobile App. The time values and graph colors do not match between both platforms. | Open
Bug-015 | Referral Credited notification is navigating to an incorrect route. correct route (Transaction) ---- current route packs | Open
Bug-016 | The search field placeholder in Reward History is incorrect. | Open
Bug-017 | Gold transfer notification is navigating to an incorrect route. correct route (Transaction) ---- current route wallet | Open
Bug-018 | Conversion notification is navigating to an incorrect route. correct route (Transaction) ---- current route wallet | Open
Bug-019 | Gold sold notification is navigating to an incorrect route. correct route (Transaction) ---- current route wallet | Open
Bug-020 | Transfer successful notification is navigating to an incorrect route. correct route (Transaction) ---- current route wallet | Open
Bug-021 | Gold purchased notification is navigating to an incorrect route. correct route (Transaction) ---- current route wallet | Open
Bug-022 | RBF Credited notification is navigating to an incorrect route. correct route (Transaction) ---- current route trc20 | Open
Bug-023 | X-axis last value blinks and disappears when zooming the graph | Open
Bug-024 | Numeric values remain in the English number format when the application language is set to Arabic. | Open
Bug-025 | Change the date sorting based on recent date (RBF volume) | Open
Bug-026 | In Support Ticket, an error occurs when the Admin tries to add a long text message. | Open
Bug-027 | The transaction PDF does not display the transaction date and time. | Open
Bug-028 | Integration of Royal Flow Control | Open
Bug-029 | Integration of Sub Account | Open
Bug-030 | Integration of Fraud Analysis | Open
Bug-031 | When a user submits a TRC20 request, an email notification should be sent to the Client with the relevant request details. | Open
Bug-032 | Mobile responsive --- admin | Open
Bug-033 | Review product | Open
Bug-034 | When the user receives reward points, the RBF value displayed in the header is not updated automatically. | Open
Bug-035 | “Change” Text Overlaps in Gold Price History on Mobile Responsive ---- market index. | Done
Bug-036 | All Packs Data Does Not Load After Language Change on Another Device | Done
Bug-037 | In mobile responsive view, the starting part of the Earn and Refer link is cut off when the application language is changed. | Done
Bug-038 | In mobile responsive view, when the application language is set to Arabic, the starting digits or characters of values displayed on Dashboard cards are cut off. | Done
Bug-039 | change label text (Total Volume Reached) to (Total balance Reached) ---- user rbf volume | Done
Bug-040 | Cart Button Appears After Refreshing the Web Page. | Done
Bug-041 | The dropdown arrows displayed in the FAQ section should change direction according to the selected language. | Done
Bug-042 | The back arrow displayed throughout the web application should change its direction when the Arabic language is selected. | Done
Bug-043 | When the app language is changed to Arabic, one withdrawal status is removed/not displayed. | Done
Bug-044 | In the Wallet section, the text “Digital Gold value ≈ 80,365.48 RBF” is not translated when the app language is changed to Arabic. | Done
Bug-045 | The FAQs alignment is incorrect when the application language is set to Arabic. | Done
Bug-046 | Some notifications are displayed in Arabic, while others are displayed in English when the application language is set to Arabic. | Done
Bug-047 | Currency: | Done
Bug-048 | The currency change slider is not functioning properly, and some currency options are not displayed. | Done
Bug-049 | When the application language is changed to Arabic, the text for transaction types such as P2P Transfer, Sell Gold, and others gets cut off. | Done
Bug-050 | There is no gap between the cards on the dashboard. | Done
Bug-051 | The Bonus History screen does not update when the application language is changed. | Done
Bug-052 | The Rank History screen does not update when the application language is changed. | Done
Bug-053 | When the user changes the application language on one device while the same account is logged in on another device, backend-driven data updates correctly, but frontend text does not update on the second device. | Done
Bug-054 | The Calendar does not update its language after the application language is changed. | Done
Bug-055 | Table Pagination Arrows Misaligned in Arabic Mobile View | Done
Bug-056 | In mobile responsive view, the Filter and Status text alignment becomes incorrect after changing the language to Arabic. | Done
Bug-057 | Changing the application language causes an excessive gap to appear before the table. | Done
Bug-058 | In mobile responsive view, the slider indicator does not work correctly after changing the application language. | Done
Bug-059 | When the language is set to Arabic and the application is viewed in mobile responsive mode, the Dashboard cards do not have the same size. | Done
Bug-060 | After changing the selected currency, the displayed values are not being converted correctly and show incorrect amounts. | Done
Bug-061 | In the Withdrawal screen, when the entered TRC20 Address does not match any saved address, the following message is displayed: No saved addresses match your search. After changing the application language, this message is not translated. | Done
Bug-062 | In Market Index, the tooltip is cut off when the application language is set to Arabic. | Done
Bug-063 | In Market Index, the tooltip language does not change when the application language is changed. | Done
Bug-064 | In the Ambassador section, the Active Members and Inactive Members text is not translated after changing the application language. | Done
Bug-065 | When the application language is set to Arabic, the Notifications section is not aligned correctly. | Done
Bug-066 | After changing the application language, the Status and Filter labels are not translated. | Done
Bug-067 | The TRC20 PDF cannot be downloaded because the feature is currently unavailable. | Done
Bug-068 | After changing the application language, the language in downloaded/generated PDFs is not updated. | Done
Bug-069 | On the Withdrawal screen, the search text is not updated after changing the application language. | Done
Bug-070 | When the application language is set to Arabic, some labels in the Table and Details sections are not translated. | Done
Bug-071 | When the application language is set to Arabic, the amount displayed in the Header is not formatted correctly. | Done
Bug-072 | Ambassador Images Are Not Displayed After Language Change | Done
Bug-073 | PDF Download Fails After Changing Language | Done
Bug-074 | Settings Description Does Not Display in a Single Line on Mobile Responsive | Done
Bug-075 | The “No Notification Yet” message remains in the default language after changing the application language. | Done
Bug-076 | The loading message displayed while notifications are being loaded does not change according to the selected language. | Done
Bug-077 | The Set Password screen remains in the default language after changing the application language. | Done
Bug-078 | The text displayed on the OTP screen does not change according to the selected language. | Done
Bug-079 | The Forgot Password screen remains in the default language after changing the application language. | Done
Bug-080 | The text on the Sign Up screen does not change according to the selected language. | Done
Bug-081 | Some content on the privacy policy screen is being translated when the language is changed | Done
Bug-082 | Some content on the Terms & Conditions screen is being translated when the language is changed | Done
Bug-083 | The text on the Edit Profile screen remains in the default language after changing the application language. | Done
Bug-084 | Validation and error messages remain in the default language after changing the application language. | Done
Bug-085 | The text displayed across the KYC flow does not change according to the selected language. | Done
Bug-086 | Toast messages remain in the default language after changing the application language. | Done
Bug-087 | The text displayed on the first card of the Ambassador Program does not change according to the selected language. | Done
Bug-088 | The “Day” text displayed in Market Index remains in the default language. | Done
Bug-089 | After changing the application language and navigating to Transactions, three additional/incorrect options are displayed in the All Types filter. | Done
Bug-090 | Some text elements on the Transaction screens remain in the default language after changing the application language. | Done
Bug-091 | After changing the application language and navigating to Transactions, an additional/incorrect option is displayed in the All Wallet filter. | Done
Bug-092 | The heading on the Withdrawal screen remains in the default language after changing the application language. | Done
Bug-093 | The confirmation popup content does not change according to the selected language. | Done
Bug-094 | The text displayed in different modals remains in the default language after changing the application language. | Done
Bug-095 | The “Download QR Code” text does not change according to the selected language. | Done
Bug-096 | The Refer and Earn screen content remains in the default language after changing the application language. | Done
Bug-097 | The “Explore Marketplace” button text does not change when the application language is changed. | Done
Bug-098 | After purchasing a Pack, the “Go to Dashboard” text remains in the default language. | Done
Bug-099 | The text displayed on the Pack Information screen does not change according to the selected language. | Done
Bug-100 | The “Buy Now” button text on the Pack screen remains unchanged after switching the application language. | Done
Bug-101 | The information tooltip displayed on the Pack screen does not change according to the selected language. | Done
Bug-102 | The language does not change on the Support screen when the user switches the application language. | Done
Bug-103 | When Arabic is selected, the layout is not displayed properly and some UI elements become misaligned or break. | Done
Bug-104 | Date & time will be added for each transaction, and Current Gold Holding will show the member’s remaining total Gold balance after every buy or sell transaction. | Done
Bug-105 | Add next rank progress section in user side also | Done
Bug-106 | Referral Code Field Should Be Locked When Code Is Auto-Populated | Done
Bug-107 | Referral Link Redirects to Web Page Instead of Signup Page | Done
Bug-108 | “Not Promoted” Type Is Missing from Ambassador Member Filter | Done
Bug-109 | Remove Type Text from User Transactions Search | Done
Bug-110 | Remove Activity Text from Ambassador Dashboard Search | Done
Bug-111 | Incorrect Error Displayed When Logging in as User from Admin | Done
Bug-112 | Incorrect Routing from Settings When KYC Is Incomplete | Done
Bug-113 | Blocked or Suspended Pack Opens Directly | Done
Bug-114 | Values Are Rounded Off in Movement Logs and User Gold History | Done
Bug-115 | Add Information Icon on Dashboard | Done
Bug-116 | Implement Pack Suspended and Pack Blocked Functionality | Done
Bug-117 | Pack Suspend Not Removed | Done
Bug-118 | Rank History Table Column Names Are Not Properly Aligned on Mobile | Done
Bug-119 | Ambassador Program Card UI Is Incorrect on Mobile Responsive | Done
Bug-120 | Pack Blocked and Pack Suspended Notifications Are Not Displayed | Done
Bug-121 | Dashboard Cards ---- Mobile Responsive | Done
Bug-122 | Reason Is Not Displayed for Suspended or Blocked Status | Done
Bug-123 | Incorrect Color for Suspended and Blocked Transaction Status | Done
Bug-124 | Remove “Monthly Volume” Text from Rank History | Done
Bug-125 | Remove “Bonus” Text from Bonus History Search Bar | Done
Bug-126 | Tier Level Decreases When Monthly RBF Volume Drops Below 10,000 | Done
Bug-127 | Weekly RBF Volume Is Incorrect | Done
Bug-128 | Monthly RBF Volume Is Rounded Off | Done
Bug-129 | Incorrect Links for Privacy Policy and Terms & Conditions | Done
Bug-130 | Tier Upgrade Message Is Cut Off | Done
Bug-131 | Incorrect Tier Levels Values | Done
Bug-132 | Signup Fails Due to termsAccepted Property Error | Done
Bug-133 | Incorrect Royalty Points When Buying a Pack | Done
Bug-134 | Multiple Users Can Stay Logged In on the Same Browser | Done
Bug-135 | Add “All Types” filter in Movement Logs | Done
Bug-136 | Add “All Types” filter in Movement Logs | Done
Bug-137 | Cancel option is displayed for transaction types other than Pack | Done
Bug-138 | Remove Duplicate Transaction ID from Movement Log Details | Done
Bug-139 | Show Recent Movement Logs at the Top | Done
Bug-140 | Dashboard Data Does Not Update After Transactions | Done
Bug-141 | Update Pending Users Card to KYC Pending | Done
Bug-142 | Remove Cancel Pack Option from Co-Founder Pack | Done
Bug-143 | The following error is displayed when attempting to Buy Gold or Sell Gold: Cannot POST /api/v1/wallet/gold/trade | Done
Bug-144 | The Sales card for services currently displays the amount in USD --- partner | Done
Bug-145 | Replace Product Category with Item Category wherever applicable. | Done
Bug-146 | The values displayed on the Dashboard Cards are not aligned on the same line. | Done
Bug-147 | The Royalty Points are calculated incorrectly when a user makes a Royal Buy purchase above 50,000. | Done
Bug-148 | KYC screen is skipped after user registration | Done
Bug-149 | Category tag is getting cut off | Done
Bug-150 | Conversion should be displayed when only the amount is entered | Done
Bug-151 | Back button on the P2P Transfer Success screen should navigate to the Wallet | Done
Bug-152 | Uploaded KYC image turns black in the Production build | Done
Bug-153 | Cart reloads twice after updating item quantity | Done
Bug-154 | User is not redirected to the Home screen after resetting the password from the Change Password flow | Done
Bug-155 | Profile image is not cleared on the Edit Profile screen before saving | Done
Bug-156 | Refresh the Partner Products screen after closing the purchase confirmation popup | Done
Bug-157 | Profile changes are not updated in the app until returning to the Dashboard | Done
Bug-158 | Apply a 30-character limit to the First Name and Last Name fields | Done
Bug-159 | Increase the height of the Name and Email section on the More screen | Done
Bug-160 | Apply a 30-character limit to the First Name and Last Name fields | Done
Bug-161 | Incorrect maximum limit is displayed for Packs | Done
Bug-162 | Initial OTP is not received, but Resend OTP works | Done
Bug-163 | Passport image cannot be replaced after upload | Done
Bug-164 | New user is redirected to the previous user's KYC Details screen | Done
Bug-165 | Wallet balance is not updated automatically after a conversion | Done
Bug-166 | Quantity value reverts when edited using the keyboard | Done
Bug-167 | Previously selected category remains selected after clearing Product Filters | Done
Bug-168 | Max amount field automatically changes the entered value | Done
Bug-169 | Heading text does not fit on a single line at 100% screen scaling | Done
Bug-170 | After refreshing the Deposit Requests screen in the Admin panel and navigating to Edit TRC20 Address, an incorrect TRC20 Address is displayed before the correct address loads. | Done
Bug-171 | Total Balance reloads repeatedly when adding items to the cart | Done
Bug-172 | In the TRC20 section, the Pending Amount and Transferred Amount currently do not have a clear visual distinction. | Done
Bug-173 | The Transfer Date is currently displayed even though the Admin has not performed the transfer yet. --- TRC20 | Done
Bug-174 | When a user selects a Country and then selects the same Country again, the related City list does not load or display. | Done
Bug-175 | In Order Management → Delivery Information, the Total Amount label should be displayed based on the currency/type associated with the order. | Done
Bug-176 | The data currently displayed in the Prestige section is incorrect and includes information that should not be present. | Done
Bug-177 | The Delivery Information section on the Web Order Details screen should follow the same design and layout currently implemented on the App. | Done
Bug-178 | In the Deposit Request → Request Detail screen, the background/container height of the displayed image does not match the approved design. | Done
Bug-179 | Remove tax amount for order detailss (prestige) | Done
Bug-180 | In the TRC20 submission flow, the Payment Proof image is not being uploaded successfully. | Done
Bug-181 | Weekly Earnings are not added to the wallet and no transaction history is generated | Done
Bug-182 | P2P Transfer dropdown size and options do not match the approved design | Done
Bug-183 | When the user adds a Royal Product to the cart, and then opens View Cart, the Cart screen loads twice. | Done
Bug-184 | Meeting Type should be optional | Done
Bug-185 | Load data when opening Dashboard and Marketplace tabs | Done
Bug-186 | In the Invitation List, there is excessive empty space below the Search Bar, which does not match the approved design. | Done
Bug-187 | Update button and navigation after submitting TRC20 | Done
Bug-188 | Remove the converted text below the field when balance is insufficient (Display Insufficient Balance message when RBF balance is not enough) | Done
Bug-189 | Display Available Balance in Buy Gold and Sell Gold | Done
Bug-190 | In Schedule Delivery, the Meeting Type text is currently displayed in bold | Done
Bug-191 | Keyboard should not open initially for Country and City dropdowns | Done
Bug-192 | After submitting a TRC20 request, the newly submitted request data does not appear automatically. The user has to manually refresh the screen to load the updated data. | Done
Bug-193 | On the TRC20 Detail screen, the Transaction ID is currently displayed in the transaction data. It should be removed. | Done
Bug-194 | The image preview should only open once the image has been fully loaded. | Done
Bug-195 | The Delete button should be hidden for all deactivated products. | Done
Bug-196 | Replace "Total RBG" with "Total Gold" on Admin Cards | Done
Bug-197 | Replace RBG text with Gold in Users header | Done
Bug-198 | Replace "Gold RBG" text with "Gold" in Admin Cards and Header | Done
Bug-199 | In Sell Gold → Transaction History, the transaction is currently displayed as net RBG Received, which is incorrect. (net recieved) | Done
Bug-200 | In Sell Gold → Transaction History, the transaction type is currently incorrect. | Done
Bug-201 | In Schedule Delivery, the Meeting Type field is optional and should not be required to submit the form. | Done
Bug-202 | For the first weekly payout, the credited Weekly Earnings should also be reflected as the Total Earnings. | Done
Bug-203 | The Admin Panel should display the correct RBF and RBG amounts received/earned by the user through transactions, including conversion fees where applicable. | Done
Bug-204 | In the Buy Gold and Sell Gold flows, the transaction summary should be displayed when the user has insufficient balance. Currently, the summary is not shown in this scenario. | Done
Bug-205 | For a pending TRC20 request, the Request ID is currently displayed below “USDT Top-Up (TRC20)”. The Request ID should not be displayed there. | Done
Bug-206 | In the Buy Gold and Sell Gold sections, the text field label is currently displayed as “Quantity” on the web. According to the design, the label should be “Gold Quantity (g)”. | Done
Bug-207 | The text displayed in the KYC rejection notification needs to be updated. Current Text: "KYC was not approved" Expected Text: "KYC has been rejected" | Done
Bug-208 | Remove refferal reward earned notification | Done
Bug-209 | Incorrect Notification Time | Done
Bug-210 | Images are appearing corrupted instead of displaying correctly. | Done
Bug-211 | The profile picture appears corrupted after being uploaded/updated (User) | Done
Bug-212 | Add text on admin dashboard (Physical gold backed ≈ 141,606 RBF) | Done
Bug-213 | “qwer” has been submitted and is awaiting approval -- partner product | Done
Bug-214 | “testtt testtttestttte sttttestt ttesttt testtt tes” was set to inactive and is no longer visible to customers. ---- product reject description partner | Done
Bug-215 | Product Rejected -- partner notification title | Done
Bug-216 | Support status change notification missing | Done
Bug-217 | 55 grams of gold has been sold, and ____ RBF has been credited to your wallet --- Gold Sold | Done
Bug-218 | Gold Purchased -- same as sold | Done
Bug-219 | Remove trailing zero from conversion notification | Done
Bug-220 | Don't show the reason in rejected order notification | Done
Bug-221 | Remove trailing zero from referral notification | Done
Bug-222 | Incorrect notifation recieved on conversion | Done
Bug-223 | Notification title capitalization issue | Done
Bug-224 | prestige order notification is not appearing | Done
Bug-225 | Review product notification is missing | Done
Bug-226 | Order ORD-9404 has been delivered. | Done
Bug-227 | Order ORD-9404 has been confirmed. | Done
Bug-228 | Amounts displayed in the Notifications should include the appropriate amount separator for better readability. | Done
Bug-229 | The data currently displayed in the Prestige section is incorrect and includes information that should not be present. | Done
Bug-230 | In Sell Gold → Transaction History, the transaction is currently displayed as RBG Received, which is incorrect. | Done
Bug-231 | The Order Source field should be removed from the Delivery Information section (order details) | Done
Bug-232 | The Sub-Total should not be displayed in Prestige Order Details. | Done
Bug-233 | The TRC20 Download action should match the Web behavior: - Display "Sorry, this feature is not available yet." - Do not display a loader for this unavailable feature. | Done
Bug-234 | Update Meeting Place and Meeting Type order in Order Details | Done
Bug-235 | After the user successfully places an order, the Cart icon still displays a count even though the cart should be empty. | Done
Bug-236 | On the TRC20 Processing screen, the transaction amount is displayed without the required number separator. | Done
Bug-237 | The input fields should support a maximum of 8 whole-number digits along with up to 4 decimal places. | Done
Bug-238 | Add Wallet filter from Transactions | Done
Bug-239 | In the P2P Transfer flow, no transfer type should be selected by default. In the P2P Transfer flow, the Amount field should not be displayed until the user selects a transfer type. | Done
Bug-240 | In the P2P Transfer flow, the entered amount is being rounded off. | Done
Bug-241 | Admin ---- If the subject exceeds the available space, it should be truncated and displayed with ellipsis (...) to maintain a clean and consistent listing layout. | Done
Bug-242 | Remove Wallet filter from Transactions | Done
Bug-243 | When a user performs a transaction, the related data displayed on the Dashboard is not updated automatically. | Done
Bug-244 | The input value should be restricted to a maximum of 8 digits, including the whole number and decimal digits as applicable. | Done
Bug-245 | The Dashboard and Header should display the exact amount without unnecessary round-off. | Done
Bug-246 | Incorrect linking on quick action | Done
Bug-247 | Remove Fee (0%) from buy gold summary | Done
Bug-248 | Add Wallet filter from Transactions | Done
Bug-249 | Entering a long amount in the Gold Quantity field during a P2P transfer breaks the Summary layout. | Done
Bug-250 | Incorrect buy and sell gold transaction detail. typekey issue | Done
Bug-251 | When the amount on the Dashboard is too large, the card layout is not displayed correctly. The unit should be moved to the next line. | Done
Bug-252 | “Purchase Gold” text will be changed to “Buy Gold.” | Done
Bug-253 | Remove conversion fee from buy gold transaction | Done
Bug-254 | Switching to another tab should also close the notification panel. | Done
Bug-255 | Clicking the notification icon should close the notification panel. | Done
Bug-256 | The Sub-Total should not be displayed in Prestige Order Details. | Done
Bug-257 | In the P2P Transfer flow, the Amount field should not be displayed until the user selects a transfer type. | Done
Bug-258 | When the user is on the second page of a paginated listing and performs any transaction, the transaction is processed successfully, but the listing remains on the second page after loading. | Done
Bug-259 | In the RBF Supply section of the Admin Panel, excessive space is displayed below the Supply Logs heading. | Done
Bug-260 | In the Edit Sub-Category screen, the text box is displayed without a visible border. | Done
Bug-261 | In the Transaction History section, the Date Range and Download options should be positioned on the right side of the Transactions heading. | Done
Bug-262 | The minimum quantity will be 1 gram, and the quantity field placeholder will also be updated accordingly. | Done
Bug-263 | When the Buy Gold or Sell Gold popup is open, pressing the Tab key changes/focuses elements in the background. The background should remain inactive while the popup is open. | Done
Bug-264 | Remove Wallet filter from Transactions | Done
Bug-265 | When clicking on notification from order detail screen, the icons appear corrupted. | Done
Bug-266 | The Product Amount is being rounded off instead of displaying the exact value. | Done
Bug-267 | Incorrent kyc title --- rejected | Done
Bug-268 | Amounts displayed in the Notifications should include the appropriate amount separator for better readability. | Done
Bug-269 | Confirm delivery notification is not appearing | Done
Bug-270 | An incorrect error message is displayed when sending gold using an invalid Wallet ID. | Done
Bug-271 | Order ORD-49838 has been rejected. -- partner notification description user | Done
Bug-272 | Your support ticket “Hiiiii” is now under review. | Done
Bug-273 | Admin replied to your support ticket --- support reply title | Done
Bug-274 | You have received a reply from the admin regarding your support ticket “HII”.. support reply description | Done
Bug-275 | Incorrect support notification ----- Your support ticket “Hiiiii” has been resolved | Done
Bug-276 | Incorrect notification text is appearing on order reject (Order ORD-3433 has been rejected) | Done
Bug-277 | Add Wallet filter from Transactions | Done
Bug-278 | Remove the 0.2% fee from the Buy Gold transaction. | Done
Bug-279 | The displayed RBF and Gold values do not match the actual/expected values. | Done
Bug-280 | The minimum quantity will be 1 gram, and the quantity field placeholder will also be updated accordingly. | Done
Bug-281 | Validation errors are displayed on the Login screen when navigating from Login → OTP and then returning to the Login screen. | Done
Bug-282 | The Buy Gold and Sell Gold text is not displayed correctly in the Transaction filter. | Done
Bug-283 | After navigating from Wallet → Deposit → TRC20 Request, clicking the Back to TRC20 button causes the back navigation button to stop working. | Done
Bug-284 | Remove the Convert button displayed at the top of the Wallet screen. | Done
Bug-285 | Remove the Sell Gold link from the Market Index. | Done
Bug-286 | Remove Fee (0%) from buy gold summary | Done
Bug-287 | Replace “My Wallet” with “Royal Wallet.” | Done
Bug-288 | When the amount on the Dashboard is too large, the card layout is not displayed correctly. | Done
Bug-289 | Incorrect buy and sell gold transaction detail. typekey issue | Done
Bug-290 | When navigating from the Login screen to the OTP screen and then pressing Back, the OTP screen appears again instead of returning to the Login screen. | Done
Bug-291 | “Purchase Gold” text will be changed to “Buy Gold.” | Done
Bug-292 | The profile picture is not updating successfully (Admin - partner) | Done
Bug-293 | Add Pull-to-Refresh to Notification List | Done
Bug-294 | Update the Buy Gold and Sell Gold quantity placeholder from “Min. 1 gram” to “e.g. 1 gram.” | Done
Bug-295 | If the Notification modal is open and the user navigates to the Cart, the Notification modal should close automatically. | Done
Bug-296 | The Total Deducted Amount is not displayed in the Transaction History for P2P transfers. | Done
Bug-297 | While the Wallet screen is loading, the container sizes are not equal. | Done
Bug-298 | Admin should be able to send RBF to any user after receiving a cash. | Done
Bug-299 | In Gold Price History, the text color of the Change value does not match the approved design. | Done
Bug-300 | Remove Space After Transfer ID in Search Placeholder ---- Transfer RBF | Done
Bug-301 | RBF transfer filter is missing in transaction (On Staging) | Done
Bug-302 | 900,000 RBF has been credited to your wallet by the admin ---- transfer credited notification description (On Staging) | Done
Bug-303 | Integration of Market Index (mene dediya h minh or ahmed ko) | Done
Bug-304 | An unwanted shadow is appearing on the right side across the Users screens. | Done
Bug-305 | Mobile Responsive --- web (FAQs) | Done
Bug-306 | Partner Products are missing in the Admin Panel. | Done
Bug-307 | About Founders and Management page returns HTTP 404 error | Done
Bug-308 | Display TRC20 listing on Deposit tab | Done
Bug-309 | Incorrect label in gold card (rbf not rbg) | Done
Bug-310 | Full stop is missing (100 RBF has been credited to your wallet by the admin) RBF Credited notification (done in staging) | Done
Bug-311 | Incorrect text displayed for Market Index History timeframe (3 months) (done in staging) | Done
Bug-312 | In the Wallet, when the user converts RBF to Gold or Gold to RBF, the transaction type is not displayed correctly. Instead of showing Conversion, it is displayed as Buy Gold or Sell Gold. (done in staging) | Done
Bug-313 | Remove unnecessary trailing zeros from Conversion successful notification (done in staging) | Done
Bug-314 | The newly uploaded profile picture is not updated immediately and takes too long to appear. | Done
Bug-315 | Add shimmer (market index options) --- 1H, 24H | Done
Bug-316 | When selecting any option from the Drawer menu, the hover/active state is not displayed correctly on the corresponding icon. | Done
Bug-317 | When performing an RBF Transfer, the borders of the input fields disappear during the transfer flow. | Done
Bug-318 | Market index graph issue (x-asix and y-axix) -- roundoff | Done
Bug-319 | When purchasing the last available pack, entering an amount higher than the minimum value causes the transfer to fail. | Done
Bug-320 | A space should be present between TRC20 and Address. --- Withdraw error message | Done
Bug-321 | Changes have been made to the Withdrawal Listing in the approved design. | Done
Bug-322 | TRC20 is not consistently displayed in uppercase. --- Withdraw | Done
Bug-323 | The error message length and formatting are incorrect. --- Withdraw | Done
Bug-324 | The withdrawal amount should not be permanently deducted while the transaction is Pending. The balance should only be deducted once the withdrawal is successfully processed. | Done
Bug-325 | Textual changes have been made to the Withdrawal Listing in the approved design. | Done
Bug-326 | The TRC20 Address is not displayed correctly in the Withdraw Details screen. | Done
Bug-327 | Withdrawal Details Are Incorrect in Transaction | Done
Bug-328 | In the Admin Deposit Request Details screen, the text overlaps when a larger amount is displayed. | Done
Bug-329 | The amount input field does not handle leading zeros correctly when editing a large decimal value. For example, when entering 10000000.9822 and removing digits after the initial 10, the 0 values are also removed unexpectedly. | Done
Bug-330 | The amount in the withdrawal flow should be displayed in USDT, not RBF. --- input field | Done
Bug-331 | Mailgun Issue | Done
Bug-332 | Withdrawal Details Are Incorrect in Transaction | Done
Bug-333 | Otp issue | Done
Bug-334 | Search and Filter controls should be hidden when there is no data --- web | Done
Bug-335 | Market index graph issue (x-asix and y-axix) --- ahmed or ibad sy recheck krwa lyna --- add time or date in tool tip | Done
Bug-336 | In Admin Withdrawal Details, the required action buttons are missing. | Done
Bug-337 | On the Admin Withdrawal screen, The Action column should provide the following options: Transferred, Reject, View Details | Done
Bug-338 | In the Transaction details, the TRC20 address is displayed twice ---- user | Done
Bug-339 | The Admin Withdrawal Details section does not display the user's Username and User ID. | Done
Bug-340 | On the Admin Withdrawal screen, the export option is currently showing XLS, which is incorrect. The required export format is PDF. | Done
Bug-341 | In Admin Withdrawal Details, the field text is showing “Transaction ID,” | Done
Bug-342 | On the User Withdrawal screen, the search field displays “Transaction ID”, which is incorrect. | Done
Bug-343 | The Withdrawal notification should route the user directly to the Withdrawal screen. | Done
Bug-344 | Currently, 1000 credits are automatically added to the user's account upon signup. This default credited amount should be removed. | Done
Bug-345 | Add minus (-) in transfer amount field -- Admin | Done
Bug-346 | In the Withdrawal Details section, the user's note is being displayed to the admin. The user's note should not be visible to the admin. | Done
Bug-347 | Currently, 1000 credits are automatically added to the user's account upon signup. This default credited amount should be removed. | Done
Bug-348 | A 10% deduction should be applied to the amount requested by the user. | Done
Bug-349 | In the Transaction section, the Deducted Amount displayed in the Withdrawal Details is incorrect. | Done
Bug-350 | The description displayed in the Withdrawal Rejected notification is incorrect. | Done
Bug-351 | In the Admin Withdrawal table, the RBF ID is currently displayed instead of the User ID. | Done
Bug-352 | For a withdrawal request of 99,999,999.9999 RBF, the system deducts 100,000,000 RBF from the user's wallet. | Done
Bug-353 | In the Withdrawal section, the Approved filter is not working. | Done
Bug-354 | The Withdrawal Details screen shows the amount as deducted even though the withdrawal request is still Pending. | Done
Bug-355 | Replace Transaction ID with Withdrawal Request ID. | Done
Bug-356 | Remove the Time from the Withdrawal PDF. | Done
Bug-357 | Add date in withdrawal pdf | Done
Bug-358 | The Wallet card design will be finalized first, and the same approved design should then be implemented consistently on both the Web and Mobile App. | Done
Bug-359 | The TRC20 image is appearing corrupted instead of displaying correctly. -- user --- deposit | Done
Bug-360 | The Co-Founder Reward Credited notification is navigating to the wrong screen. | Done
Bug-361 | The same Weekly Earning and Total Earned values are displayed across all packs instead of showing the actual values for each individual pack. | Done
Bug-362 | The values displayed for Weekly Earning and Total Earned are incorrect. (rahinanawab1@yopmail.com) | Done
Bug-363 | A Copy icon is required for the values displayed on the detail page, including the TRC20 Address. | Done
Bug-364 | Remove Plus Sign from Platinum Service Pack | Done
Bug-365 | Automatic referral code | Done
Bug-366 | Remove Physical Gold message from Add to Cart. | Done
Bug-367 | On the mobile responsive landing page, the drawer displays “Welcome to Royal” instead of the correct name. | Done
Bug-368 | On mobile responsive view, there is an issue when attempting to close the Drawer or Notification Modal. | Done
Bug-369 | The alignment of the Tier Levels section is not correct. | Done
Bug-370 | Incorrect session data is displayed. | Done
Bug-371 | Mobile Responsive ---- reset password | Done
Bug-372 | Mobile Responsive --- OTP screen | Done
Bug-373 | Mobile Responsive ---- TRC20 | Done
Bug-374 | Mobile Responsive ---- withdrawal | Done
Bug-375 | Remove Conversion Fee from Sell Gold Details | Done
Bug-376 | Mobile Responsive ---- all packs | Done
Bug-377 | Incorrect Android Version Displayed for Chrome Browser Session | Done
Bug-378 | The user's session remains marked as Active in the Active Sessions section even after the user has logged out. | Done
Bug-379 | Mobile Responsive ---- download QR code | Done
Bug-380 | Mobile Responsive ---- wallet | Done
Bug-381 | Mobile Responsive ---- dashboard | Done
Bug-382 | Integration of Royal Movement logs | Done
Bug-383 | Integrate the Gold Price API throughout the Gold module | Done
Bug-384 | Integrate a real-time Gold Price API to display the current gold price. | Done
Bug-385 | The modals displayed on the Wallet screen are not properly responsive across different screen sizes. | Done
Bug-386 | The cards displayed on the Wallet screen are not properly responsive on mobile devices. | Done
Bug-387 | The “Fee: 0%” label should be removed from the RBF to Gold conversion screen. | Done
Bug-388 | The “Fee: 0%” label should be removed from the RBF to Gold conversion screen. | Done
Bug-389 | The RBF Per Gram price is displayed inconsistently across different sections of the application. In some places, it is shown as 141.33, while in others it is displayed as 141.3265. | Done
Bug-390 | In the RBF to Gold conversion, the conversion rate is currently displayed incorrectly. The correct conversion value should be: 1 RBF = 0.007076 g Gold | Done
Bug-391 | The placeholder text for the Sub Category Title field in both Add Sub Category and Edit Sub Category needs to be updated. | Done
Bug-392 | The Support Title field should have a maximum character limit of 255. Users should not be able to enter more than 255 characters. | Done
Bug-393 | RBG amount is displayed without its required unit ---- users | Done
Bug-394 | The Support Title field should have a maximum character limit of 255. Users should not be able to enter more than 255 characters. | Done
Bug-395 | Login fields are not cleared when navigating back from the Verification screen | Done
Bug-396 | Hide Search and Filter controls while the Invitation List is in the loading state | Done
Bug-397 | Unexpected border is displayed around the Quantity text field | Done
Bug-398 | Set the Support Message character limit to 500 | Done
Bug-399 | The Review Title field should have a maximum character limit of 255. Users should not be able to enter more than 255 characters. | Done
Bug-400 | Set the Review Message character limit to 1000 | Done
Bug-401 | Display "-" for Transaction ID in pending Deposit Requests (pdf) | Done
Bug-402 | When a user registers in the RBF application but does not verify their email, attempting to register again with the same email address redirects the user to the Verification screen. As per the requirement, the system should display an "Email already exist | Done
Bug-403 | Suspended user is not logged out after being suspended by the Admin | Done
Bug-404 | If a user registers but does not verify their account, and the Admin suspends that user before verification, the user is still able to complete the verification process and access the Dashboard. Suspended users should not be allowed to verify their accoun | Done
Bug-405 | When a user enters a very long value in the Subject field of the Support module, the application returns an Internal Server Error instead of validating the input. | Done
Bug-406 | Whenever navigating to the Notifications screen, the notification list should load from the top. | Done
Bug-407 | Gold unit is cut off on Dashboard | Done
Bug-408 | kyc approved notification is navigating to an incorrect route. correct route all kyc verification | Done
Bug-409 | kyc submitted notification is navigating to an incorrect route. correct route all kyc verification | Done
Bug-410 | kyc rejected notification is navigating to an incorrect route. correct route all kyc verification | Done
Bug-411 | kyc not approved notification is navigating to an incorrect route. correct route all kyc verification | Done
Bug-412 | Notification are appearing twice --- mobile | Done
Bug-413 | After an order is placed successfully, the Order Placed Successfully popup is displayed. If the user then navigates to the Order Details screen through a notification, the success popup remains visible. | Done
Bug-414 | RBF service pack activated notification is navigating to an incorrect route. correct route all packs | Done
Bug-415 | Review Product notification is navigating to an incorrect route. correct route order details | Done
Bug-416 | Review Product notification is navigating to an incorrect route. | Done
Bug-417 | KYC Submitted notification is missing its routing. | Done
Bug-418 | Product price slider behavior is inconsistent with the mobile app (0 - 217) | Done
Bug-419 | Add "Min" and "Max" placeholders to the Product Filter price range fields | Done
Bug-420 | Web session is not logged out after password reset initiated from the app | Done
Bug-421 | Update the Sort By dropdown options in the Product Filter | Done
Bug-422 | Keyboard overlaps the price range fields in the Product Filter | Done
Bug-423 | Price range input resets to 1000 after entering a higher value | Done
Bug-424 | Maintain consistent spacing between products on all Order screens | Done
Bug-425 | Amount is missing from the Order Summary | Done
Bug-426 | Filters, search, and date values are not reset after navigating back (support) | Done
Bug-427 | Add all transaction types available in the app | Done
Bug-428 | Display thousand separators for all amount values | Done
Bug-429 | Remove trailing zero after the decimal point from amount values | Done
Bug-430 | Application crashes when accessing Forgot Password from Change Password on the Web | Done
Bug-431 | Display a full-screen loader while the Wallet screen is loading | Done
Bug-432 | Schedule Delivery bottom sheet closes despite missing required fields | Done
Bug-433 | Transaction ID is displayed multiple times in Pack transaction details | Done
Bug-434 | Date and Time text are missing from the Conversion transaction bottom sheet | Done
Bug-435 | Back navigation from Forgot Password screens should not redirect to the Login screen | Done
Bug-436 | Back navigation from Forgot Password screens should not redirect to the Login screen | Done
Bug-437 | Display a placeholder while the KYC image is loading | Done
Bug-438 | Premium Pack purchase fails for higher amount values | Done
Bug-439 | Long category names should wrap to the second line in the Product Filter | Done
Bug-440 | Password reset redirects to the Admin portal when creating a Partner account | Done
Bug-441 | Transaction Details screen does not match the approved design | Done
Bug-442 | Long category and subcategory names are not fully displayed on the Create/Edit Product screen | Done
Bug-443 | Truncate long text with an ellipsis | Done
Bug-444 | Disable scrolling when no data is available | Done
Bug-445 | Require category selection before creating a subcategory | Done
Bug-446 | Admin should add notes multiple times on a support ticket | Done
Bug-447 | Admin is able to log in through the User portal | Done
Bug-448 | User is always redirected to the KYC screen after login | Done
Bug-449 | OTP is not received after tapping "Resend" | Done
Bug-450 | Do This Later incorrectly navigates to the KYC screen | Done
Bug-451 | Add a Login button to the Landing Page | Done
Bug-452 | Update the video on the Landing Page | Done
Bug-453 | Export Report is not working on the Support screen | Done
Bug-454 | Numbers are missing in the Orders PDF | Done
Bug-455 | PDF download is not working (transaction) | Done
Bug-456 | Numbers are missing in the KYC PDF | Done
Bug-457 | Display Pending, Approved, and Rejected statuses for Partner products | Done
Bug-458 | Incorrect arrow symbol is displayed in the Conversion PDF | Done
Bug-459 | Explore Marketplace and "Explore Products" buttons should navigate to the Marketplace | Done
Bug-460 | Transaction filters are not working | Done
Bug-461 | Stock Left should be displayed in title case | Done
Bug-462 | Add button is displayed for out-of-stock products | Done
Bug-463 | Search state is not reset after returning from a "No Results Found" search | Done
Bug-464 | Apply an 8-digit input limit to Amount fields in conversion | Done
Bug-465 | Add a "Clear All" button to the Product Filter | Done
Bug-466 | Allow manual price entry in the "From" and "To" fields of the Product filter | Done
Bug-467 | Filters should remain disabled until products are fully loaded | Done
Bug-468 | Add Royal and Prestige filters to the My Orders screen | Done
Bug-469 | Verification tick is not displayed for approved KYC | Done
Bug-470 | Display all product names in capitalized | Done
Bug-471 | Display all product names in capitalized | Done
Bug-472 | Remove the "Cancelled" status from the My Orders screen | Done
Bug-473 | Remove the "Cancelled" status from the My Orders screen | Done
Bug-474 | Add bottom spacing on the Product Listing screen | Done
Bug-475 | Prevent adding more than the available product quantity | Done
Bug-476 | Product Details should display the default quantity and "Add to Cart" button when the cart quantity is below the maximum | Done
Bug-477 | Allow manual entry of item quantity | Done
Bug-478 | RBF balance should not be abbreviated in millions or billions | Done
Bug-479 | Display RBG amounts in grams (g) in the Wallet | Done
Bug-480 | Display a "Sort By" option before selecting a sorting method | Done
Bug-481 | Add additional sorting options to the Product filter | Done
Bug-482 | Oldest filter is not working on the Product Listing screen | Done
Bug-483 | Oldest filter is not working on the Product Listing screen | Done
Bug-484 | Oldest filter is not working on the Product Listing screen | Done
Bug-485 | Display the correct currency based on the product type | Done
Bug-486 | Replace USDT with RBF and RBG in the Product filter | Done
Bug-487 | Replace USDT with RBF and RBG in the Product filter | Done
Bug-488 | Default price range should be 0–1000 in the Product filter | Done
Bug-489 | Default price range should be 0–1000 in the Product filter | Done
Bug-490 | Do not display a separate Transaction ID for Conversion transactions | Done
Bug-491 | RBF RBG label is missing on the Conversion | Done
Bug-492 | User should remain logged in when navigating from Change Password to Forgot Password | Done
Bug-493 | Pre-fill email on the Forgot Password screen when navigated from Change Password | Done
Bug-494 | When navigating from the Change Password screen to the Forgot Password screen, the user's email address is pre-filled but remains editable. | Done
Bug-495 | KYC record order changes after approval or rejection by Admin | Done
Bug-496 | Long filter text breaks the UI on the Product Listing screen | Done
Bug-497 | KYC file upload accepts files larger than 5 MB | Done
Bug-498 | Add Pull-to-Refresh functionality on the KYC Details screen | Done
Bug-499 | Rejected reason is not displayed after KYC rejection | Done
Bug-500 | KYC image dimensions are incorrect on the KYC Details screen --- admin | Done
Bug-501 | KYC status should display "Pending" | Done
Bug-502 | ID should be displayed in uppercase on the KYC Details screen | Done
Bug-503 | P2P Transfer screen becomes unresponsive after navigating back | Done
Bug-504 | Incorrect initial error message is displayed on the P2P Transfer screen | Done
Bug-505 | Incorrect button text on the P2P Transfer Failed screen | Done
Bug-506 | Keyboard overlaps the text field on the Review screen | Done
Bug-507 | Incorrect conversion rate displayed as "1 RBF = 0 RBG" | Done
Bug-508 | Edit Profile screen is missing field validations | Done
Bug-509 | Apply an 8-digit input limit to Amount fields in P2P Transfer and Service Pack | Done
Bug-510 | Apply an 8-digit input limit to Amount fields in P2P Transfer and Service Pack | Done
Bug-511 | Bottom navigation bar disappears after changing the password | Done
Bug-512 | Verification tick should not displays on the KYC Details screen for approved KYC | Done
Bug-513 | Session expires on the Change Password screen | Done
Bug-514 | Delivery Date should not be displayed for Prestige orders | Done
Bug-515 | Delivery Date column should not be displayed in Order Management for the Partner flow | Done
Bug-516 | Long order details should be truncated with ellipsis in Prestige Marketplace | Done
Bug-517 | Incorrect order image is displayed temporarily on the My Orders screen | Done
Bug-518 | Web application crashes when entering long text in Meeting Place and Delivery Instructions | Done
Bug-519 | Long text breaks the UI in Meeting Place and Delivery Instructions fields | Done
Bug-520 | Inconsistent Premium Plan payment behavior between Web and App | Done
Bug-521 | Add Pull-to-Refresh functionality on the Wallet screen | Done
Bug-522 | Previous dates should be disabled in the Delivery Date picker | Done
Bug-523 | Add button is displayed for out-of-stock products | Done
Bug-524 | Long product description breaks the UI | Done
Bug-525 | Create Product button width is too large | Done
Bug-526 | Confirm Delivery button is displayed before the final delivery step | Done
Bug-527 | Back button does not work after purchasing a Prestige product | Done
Bug-528 | Disable the "+" button when the maximum product quantity is reached | Done
Bug-529 | Incorrect confirmation message is displayed when Admin marks an order as Delivered | Done
Bug-530 | Waiting Approval status color is incorrect on the My Orders screen | Done
Bug-531 | Delivery Information should be empty when opening the Checkout screen | Done
Bug-532 | Keyboard covers the Delivery Instructions field | Done
Bug-533 | RBG balance overflows outside the Wallet text box | Done
Bug-534 | Available Balance and Insufficient Balance states are missing in P2P Transfer | Done
Bug-535 | Back navigation from Conversion Success/Failed screen is incorrect | Done
Bug-536 | Amount calculations are not displayed without entering a Wallet ID in P2P Transfer | Done
Bug-537 | Exit confirmation dialog is missing when leaving P2P Transfer with unsaved data | Done
Bug-538 | Calculated values should be cleared when the Amount field is empty in P2P Transfer | Done
Bug-539 | Amount field should allow a maximum of 8 digits in P2P Transfer | Done
Bug-540 | Incorrect text color for Amount and Category on the Cart screen | Done
Bug-541 | Input field remains focused after keyboard is dismissed | Done
Bug-542 | Keyboard should dismiss when tapping outside the input field | Done
Bug-543 | Wallet balance should not display unnecessary decimal places for zero RBF | Done
Bug-544 | Conversion Failed screen is missing | Done
Bug-545 | Incorrect RBF conversion rate is displayed | Done
Bug-546 | Conversion screen displays incomplete text | Done
Bug-547 | Conversion values should reset when switching units in RBF/RBG Conversion | Done
Bug-548 | Add a clear (✕) button to the Date filter on the Transactions screen | Done
Bug-549 | Time is missing in Pack Purchase transaction details | Done
Bug-550 | Amount is displayed with unnecessary trailing zero | Done
Bug-551 | Duration is missing in Pack transaction details | Done
Bug-552 | Do not display decimal places when the value has no decimal fraction (transaction) | Done
Bug-553 | Recent Transactions bottom sheet does not open in Wallet | Done
Bug-554 | Incorrect validation message is displayed for the Review Message field | Done
Bug-555 | View all text should be displayed in lowercase on the Products screen | Done
Bug-556 | Review Title and Message validations are missing | Done
Bug-557 | Scrolling is not working on the Product Listing screen (filter) | Done
Bug-558 | Item name should use initial capitalization | Done
Bug-559 | End Date should be removed from P2P Transfer Received | Done
Bug-560 | Verification tick should not be displayed for users without KYC | Done
Bug-561 | View All navigates to Category instead of Product Listing | Done
Bug-562 | New user registration fails with server error | Done
Bug-563 | First Name and Last Name field validation does not work correctly for maximum character limit | Done
Bug-564 | User is automatically logged out after 10 minutes | Done
Bug-565 | Withdrawal screen button does not match the approved design | Done
Bug-566 | No Result Found message is not center-aligned on the Support screen | Done
Bug-567 | Transaction filter bottom sheet spacing issue | Done
Bug-568 | Price filter size is incorrect on the Product Listing screen | Done
Bug-569 | Reviewer name initials are not capitalized | Done
Bug-570 | RBF screen does not load correctly and Cart icon is displayed during loading | Done
Bug-571 | Incorrect spelling of "P2P Transfer" in Wallet | Done
Bug-572 | RBF Packs are displayed in the incorrect order and tile colors do not match the design | Done
Bug-573 | Incorrect minimum and maximum limits configured for the 50,000 RBF Pack | Done
Bug-574 | Number field does not accept input while purchasing an RBF Service Pack | Done
Bug-575 | Newly created user is assigned 0 RBF | Done
Bug-576 | New user creation fails with "Unauthorized" error | Done
Bug-577 | Plus (+) sign is missing with Service Pack amount | Done
Bug-578 | Login form data is not cleared after registering a new account and logging out | Done
Bug-579 | Incorrect spelling of "Packs" on Total Weekly Earnings card. Dashboard | Done
Bug-580 | Incorrect validation message is displayed for invalid OTP | Done
Bug-581 | First Name and Last Name fields should use initial capital keyboard | Done
Bug-582 | Unable to sign up due to incorrect internet connection error | Done
Bug-583 | Keyboard hides text fields on authentication screens | Done
Bug-584 | Onboarding screens are missing | Done
Bug-585 | Support list table is not displayed in Mobile Responsive view | Done
Bug-586 | Filter control size changes after selecting an option in Mobile Responsive view | Done
Bug-587 | Search box height does not match the approved design in Mobile Responsive view | Done
Bug-588 | Text field zooms in when focused in Mobile Responsive view | Done
Bug-589 | Admin notes are not visible to the user | Done
Bug-590 | Admin should not add notes multiple times on a support ticket | Done
Bug-591 | RBF Logs display receiver transaction history before sender transaction history | Done
Bug-592 | No actions should be allowed after a ticket is resolved | Done
Bug-593 | Incorrect transaction type is displayed in RBF Supply when purchasing a Service Pack | Done
Bug-594 | PDF export does not handle long data correctly | Done
Bug-595 | Text alignment is incorrect on Product Details and cart screen | Done
Bug-596 | Incorrect Product status values are displayed | Done
Bug-597 | Partner login flow should require email registration before password reset | Done
Bug-598 | Sub Category Edit modal does not display long data correctly | Done
Bug-599 | Long Category Title should be truncated with ellipsis | Done
Bug-600 | Category Title field should enforce a maximum limit of 150 characters | Done
Bug-601 | Volume is not displayed on Product Details screen in Admin Panel | Done
Bug-602 | Incorrect validation message is displayed when entering letters in Amount and Volume fields | Done
Bug-603 | Incorrect validation error is displayed when selecting Approved or Rejected filters on Products screen | Done
Bug-604 | Product cards are missing on the Product screen | Done
Bug-605 | Newly added Categories and Sub Categories should appear at the top of the list | Done
Bug-606 | Product amount should be displayed in Dollars instead of RBG (partner product) | Done
Bug-607 | Incorrect actions are displayed on the View Sub Category screen | Done
Bug-608 | Partner should not be able to log in when status is Pending or Suspended | Done
Bug-609 | Partner is unable to log in due to invalid OTP error | Done
Bug-610 | Scrolling is not working on the Create Partner screen | Done
Bug-611 | Incorrect page size/layout in Users PDF export | Done
Bug-612 | Incorrect export time displayed in Users PDF | Done
Bug-613 | Export Report functionality is not working | Done
Bug-614 | KYC search does not work with user's full name | Done
Bug-615 | Data is cleared when changing page size limit | Done
Bug-616 | Incorrect toast message is displayed when changing Pack status | Done
Bug-617 | Number counter should be removed from Royalty Points field | Done
Bug-618 | Service Pack values should display only two decimal places | Done
Bug-619 | Landing page -- Responsive issue | Done
Bug-620 | Landing page -- Mobile responsive – email input causes zoom and keyboard behavior issue | Done
Bug-621 | Landing page -- Favicon is missing from the application | Done
Bug-622 | Landing page -- Social media icons incorrectly navigate to top of the page | Done
Bug-623 | Landing page -- Join Waitlist link is missing in Privacy Policy and Terms & Conditions | Done
Bug-624 | Landing page -- Web layout missing left and right padding | Done
Bug-625 | Landing page -- Email placeholder is not fully displayed | Done
Bug-626 | Landing page -- Logo does not have a clickable link | Done
Bug-627 | Landing page -- RBF Marketplace image position does not match the approved design | Done
Bug-628 | Landing page -- Background color does not match the approved design | Done
Bug-629 | Landing page -- Email text box color does not match the approved design | Done
Bug-630 | Landing page -- Email text is truncated in banner due to insufficient container size | Done
Bug-631 | Royal Flow Control screen does not match the approved design | Done
Bug-632 | Royal Movements Log screen does not match the approved design | Done
Bug-633 | Add Notes modal in Support Details does not match the approved design | Done
Bug-634 | Support Detail screen does not match the approved design | Done
Bug-635 | Support – Actions UI does not match the approved design | Done
Bug-636 | Support – Status colors do not match the approved design | Done
Bug-637 | KYC rejected toast message does not match design | Done
Bug-638 | Reject This KYC popup does not match the design | Done
Bug-639 | KYC status does not match the approved design | Done
Bug-640 | Withdrawal Approval user avatars do not match design | Done
Bug-641 | Module screens do not open from the top of the page | Done
Bug-642 | Suspend User toast message icon does not match design | Done
Bug-643 | Users dropdown contains duplicate Users menu item | Done
Bug-644 | Cancel button border color is incorrect in delete confirmation popup | Done
Bug-645 | Action buttons do not match approved UI design | Done
Bug-646 | Label displays unwanted space between asterisk (*) and text | Done
Bug-647 | Values do not update when changing conversion type | Done
Bug-648 | Verify Your Identity – Submit for Review button state does not match design | Done
Bug-649 | Verify Your Identity – Scroll is missing | Done
Bug-650 | Verify Your Identity – Tick position is incorrect under images | Done
Bug-651 | Verify Your Identity – Image shadow appears incorrectly | Done
Bug-652 | Verify Your Identity – National ID and Passport icon boxes mismatch design | Done
Bug-653 | FAQ arrow icon size mismatch | Done
Bug-654 | FAQ screen padding issue | Done
Bug-655 | Email field should be disabled in Edit Profile | Done
Bug-656 | Submit button design mismatch in product details | Done
Bug-657 | See all reviews button design mismatch | Done
Bug-658 | Product quantity minus button not disabled at 1 | Done
Bug-659 | Product filter bottom sheet spacing issue | Done
Bug-660 | Product price unit color mismatch | Done
Bug-661 | Radio button design mismatch in filters | Done
Bug-662 | Product listing search bar design mismatch | Done
Bug-663 | My Orders filter bottom sheet spacing issue | Done
Bug-664 | My Orders search bar design mismatch | Done
Bug-665 | Support filter tick icon pixel issue | Done
Bug-666 | Support filter bottom sheet spacing issue | Done
Bug-667 | Add icon should not shown in bottom area when Create Ticket is enabled. | Done
Bug-668 | Create Ticket button hides search and filter | Done
Bug-669 | Support search bar design mismatch | Done
Bug-670 | My Referrals levels positioning incorrect | Done
Bug-671 | Refer & Earn sliders misaligned | Done
Bug-672 | Bonus level card size too large | Done
Bug-673 | Refer & Earn heading missing Bonus level label | Done
Bug-674 | Arrow icons size mismatch in More screen | Done
Bug-675 | More screen padding missing | Done
Bug-676 | Filter "Clear All" text casing incorrect | Done
Bug-677 | Incorrect label "withdrawal" instead of "withdrawals" | Done
Bug-678 | Transaction search bar design mismatch (text color) | Done
Bug-679 | Transaction search and filter field size mismatch | Done
Bug-680 | Transaction filter text color mismatch | Done
Bug-681 | Wallet card text color mismatch | Done
Bug-682 | Empty state missing View All in recent transactions | Done
Bug-683 | Withdraw button color mismatch in wallet | Done
Bug-684 | Wallet sliders misaligned | Done
Bug-685 | Navigation bar icons mismatch design | Done
Bug-686 | RBF confirmation screen missing | Done
Bug-687 | Connect Wallet button misaligned in bottom sheet | Done
Bug-688 | RBF service pack color mismatch | Done
Bug-689 | All Packs screen missing scroll | Done
Bug-690 | View All Packs text too small on dashboard | Done
Bug-691 | Font inconsistency across app | Done
Bug-692 | Dashboard sliders partially visible | Done
Bug-693 | Bottom navigation bar not fully visible | Done
Bug-694 | KYC screens missing | Done
Bug-695 | Verify Your Identity – Box size does not match design | Done
Bug-696 | Buttons and text misaligned at screen bottom | Done
Bug-697 | Do this later text capitalization issue | Done
Bug-698 | Email verification heading capitalization issue | Done
Bug-699 | Password eye icon does not match design | Done
Bug-700 | I am agree text incorrect on sign up screen | Done
Bug-701 | Keyboard overlaps text field | Done
Bug-702 | Validation error message is truncated | Done
Bug-703 | Validation error causes text field UI shift | Done
Bug-704 | Sign up heading font mismatch | Done
Bug-705 | Placeholder color mismatch in text fields | Done
Bug-706 | Terms & Conditions and Privacy Policy links not clickable | Done
Bug-707 | Onboarding reappears after back navigation from Create Account/Login | Done
Bug-708 | Packages image mismatch on onboarding 2nd screen | Done
Bug-709 | Font size issue on onboarding screen | Done
Bug-710 | Login button color mismatch on onboarding screen | Done
Bug-711 | Conversion values between 1 and 1.9 are not displayed correctly | Done
Bug-712 | Ticket submission incorrectly requires a minimum of 9 characters | Done
Bug-713 | Show proper "Insufficient Balance" message in P2P Transfer | Done
Bug-714 | Pack pricing text should be center aligned | Done
Bug-715 | Incomplete data displayed in Transaction Details | Done
Bug-716 | Pack information missing in Complete Transaction Details | Done
Bug-717 | PDF should not be generated when no data is available | Done
Bug-718 | Need staging, production separate environment | Done
Bug-719 | UI breaks when entering excessively long values | Done
Bug-720 | Conversion fails with incorrect "Insufficient Balance" error | Done
Bug-721 | Balance does not update after receiving a transfer | Done
Bug-722 | P2P transfer fails with incorrect "Insufficient Balance" error | Done
Bug-723 | Increment (+) control appears twice on amount | Done
Bug-724 | Platinum Pack shows maximum value validation despite displaying "No Limit" | Done
Bug-725 | Pack amount updates automatically while entering amount | Done
Bug-726 | Silver Pack maximum amount validation not enforced | Done
Bug-727 | Invalid Amount error shown when amount field is empty | Done
Bug-728 | Forgot Password navigates to OTP screen for non-existent user | Done
Bug-729 | Validation errors persist after reopening modal | Done
Bug-730 | Show exit confirmation when closing a modal with unsaved changes | Done
Bug-731 | Modal should not close when clicking outside of it | Done
Bug-732 | Error messages should start with a capital letter | Done
Bug-733 | Forgot Password not working from Change Password screen | Done
Bug-734 | Incorrect password error persists while typing in Current Password field | Done
Bug-735 | KYC checkmark should not appear for unregistered users | Done
Bug-736 | Profile picture updates without clicking Save in Edit Profile | Done
Bug-737 | Save button should remain disabled until changes are made | Done
Bug-738 | Dashboard does not open from the top after login | Done
Bug-739 | Enter key should trigger Sign In and Sign Up actions | Done
Bug-740 | Forgot Password resend code not received via email | Done
Bug-741 | Incorrect "Email already verified" error when resending code in Forgot Password | Done
Bug-742 | Dashboard refresh shows "Page Not Found" error | Done
Bug-743 | Name initials should be automatically capitalized | Done
Bug-744 | Resend OTP button text changes to "Verifying" temporarily | Done
Bug-745 | Terms & Conditions and Privacy Policy pages are missing | Done
Bug-746 | Reviews Text Styling Issue | Done
Bug-747 | Incorrect Wallet Type Sheets | Done
Bug-748 | Ratings Section UI Issue | Done
Bug-749 | Minus button behavior incorrect | Done
Bug-750 | Gold Bars Text Color Issue | Done
Bug-751 | Marketplace Images Not Showing | Done
Bug-752 | Admin Response text Mismatch | Done
Bug-753 | Support Text Color Mismatch | Done
Bug-754 | My Referrals Alignment Issue | Done
Bug-755 | Bonus Level Text Alignment Issue | Done
Bug-756 | Extra Items in Sheets | Done
Bug-757 | Missing RBF Reward Points Sheet | Done
Bug-758 | Recent Transactions Text Style Issue | Done
Bug-759 | P2P Transfer Lock Icon Misalignment | Done
Bug-760 | Email Field Not Editable (UI Issue) | Done
Bug-761 | Missing Validation on Change Password | Done
Bug-762 | Missing Forgot Password Link | Done
Bug-763 | Quick Action Icons Mismatch | Done
Bug-764 | Incorrect Capitalization in National ID | Done
Bug-765 | Missing File Format & Size Text | Done
Bug-766 | Missing Tick/Cross on Identity Verification | Done
Bug-767 | Confirm Password Validation Issue | Done
Bug-768 | Missing Email & OTP Verification Screen | Done
Bug-769 | Inconsistent Email & Password Validation | Done
Bug-770 | Need staging, production separate environment | Done
Bug-771 | Incorrect Sign Up Text | Done
Bug-772 | UI Misalignment (Button & Logo) | Done
Bug-773 | Button Gradient Mismatch (Whole Web) | Done
Bug-774 | Display "Approved" as the KYC status consistently (Admin Flow) | Done
Bug-775 | Display "Approved" as the KYC status consistently (User Flow) | Done
Bug-776 | Display thousand separators for all amount values | Done
Bug-777 | The filters available in the Ambassador module do not match the approved requirements/design. | Done
Bug-778 | Incorrect Sign In Text | Done
Bug-779 | Multiple product names are not displayed in Orders and Transactions | Done
Bug-780 | Only one category is displayed in Transaction Details for orders with multiple categories | Done
Bug-781 | Incorrect Order ID is displayed in Transaction Details | Done
Bug-782 | KYC status is inconsistent between User Details and KYC Details | Done
Bug-783 | Inactive product should be removed from the cart automatically | Done
Bug-784 | Incorrect error message is displayed when Product Sub Category is not selected | Done
Bug-785 | Revamp the RBF Supply Logs and remove the Transaction ID | Done
Bug-786 | Rejected reason is not displayed after KYC rejection – Admin | Done
Bug-787 | KYC Details screen does not match the approved design | Done
Bug-788 | Incorrect formatting of text in search results (RBF Supply) | Done
Bug-789 | Incorrect color is displayed for the "Approved" status in the Ambassador module | Done
Bug-790 | Details screen slider is not fully visible | Done
Bug-791 | Excessive spacing between name and email in User KYC Details | Done
Bug-792 | Ellipsis ("...") is displayed after the Delivery Status in My Orders | Done
Bug-793 | Users --- Ellipsis ("...") is displayed after the Transaction Type in Transaction. | Done
Bug-794 | Active Members text is cut off on the card | Done
Bug-795 | Incorrect icon is displayed for the Ambassador Program in the Drawer | Done
Bug-796 | FAQs option (drawer) and screen are missing | Done
Bug-797 | Tier level cards are cut off on the screen | Done
Bug-798 | UI shifts after selecting a filter ---- Request logs | Done
Bug-799 | Ambassador Dashboard dropdown options are displayed in the incorrect order | Done
Bug-800 | Incorrect comma placement in the "Search by User , Activity" label | Done
Bug-801 | The Drawer displays "Users" instead of the required "Ambassador User Listing" label. | Done
Bug-802 | User Network Details screen does not match the approved design | Done
Bug-803 | The Drawer displays "Ambassador" instead of the required "Ambassador Dashboard" label. | Done
Bug-804 | Incorrect menu label is displayed for the Ambassador Users section in the Drawer | Done
Bug-805 | Incorrect menu label is displayed in the Drawer (Ambassador Dashboard) | Done
Bug-806 | Incorrect card color is displayed for Level 3 in the Royal Network | Done
Bug-807 | Tier level image does not match the displayed tier name | Done
Bug-808 | Amount field automatically changes large numeric values (P2P transfer input field) | Done
Bug-809 | Silver Pack purchase succeeds despite insufficient RBF balance | Done
Bug-810 | Plus (+) sign should not be displayed in Reward History amounts | Done
Bug-811 | Statuses with 0% are displayed in the Member Status pie chart | Done
Bug-812 | The Member Status pie chart calculates and displays incorrect percentage values. For example, a segment that should display 50% is displayed as 100%. | Done
Bug-813 | Download and Date Range options should be removed from the Invitation List | Done
Bug-814 | Invitation List does not match the approved design when there are no invitations | Done
Bug-815 | Date, filters, and search are displayed when Reward History is empty | Done
Bug-816 | Referral link text color does not match the approved design | Done
Bug-817 | Convert USDT to TYX option should be removed from the Conversion screen | Done
Bug-818 | The P2P Transfer screen displays a 0.5% transfer fee, whereas the required fee is 0.2%. | Done
Bug-819 | Incorrect color is displayed for the "Approved" status in the Invitation List | Done
Bug-820 | Member Status option colors do not match the approved design | Done
Bug-821 | In the Referral Details screen, the Bonus amount displays decimal places when its value is 0. | Done
Bug-822 | The Invitation List displays the KYC status as Verified, whereas the correct status should be Approved. | Done
Bug-823 | On the USDT Top-Up (TRC20) flow, an extra confirmation popup is displayed before the Top-Up Request Submitted success screen. This popup is not required. | Done
Bug-824 | Shimmer loading is missing (+) trc20 | Done
Bug-825 | Maximum 8-digit validation is missing for Request Amount and Transfer Amount fields | Done
Bug-826 | Shimmer loading is missing for sliders dots --- refer and earn | Done
Bug-827 | Amount separator is missing in the P2P Transfer amount field | Done
Bug-828 | Amount separator is missing in the retuest and transfer amount | Done
Bug-829 | TRC20 description text color does not match the approved design | Done
Bug-830 | The P2P Transfer screen displays a 0.5% transfer fee, whereas the required fee is 0.2%. | Done
Bug-831 | Display the disabled Email field in grey | Done
Bug-832 | User ---- Forgot Password flow redirects to Login after Email Verification | Done
Bug-833 | Partner should be logged out immediately after account suspension | Done
Bug-834 | Display "Sending OTP" immediately after tapping Resend OTP | Done
Bug-835 | The "Referral Link Copied" message is displayed in the Ambassador module after copying the referral link. This message should not be shown. | Done
Bug-836 | On the Order Details screen, when the Product dropdown is collapsed, one product should remain visible instead of hiding all products. | Done
Bug-837 | During RBF conversion, the converted RBF value is being rounded off instead of displaying the correct calculated value. | Done
Bug-838 | The Close (X) button on the Placed Order Successfully popup does not follow the required navigation flow. | Done
Bug-839 | TRC20 Transaction History displays empty data | Done
Bug-840 | The value entered in Transfer Amount should automatically populate the Request Amount field. | Done
Bug-841 | Shimmer loading is missing for sliders dots --- ambassador | Done
Bug-842 | Shimmer loading is missing for sliders dots --- wallet | Done
Bug-843 | Request Amount field should appear below it with the unit RBF. | Done
Bug-844 | Transfer Amount field should appear first with the unit USDT. | Done
Bug-845 | Member count is not displayed in the Member Status section | Done
Bug-846 | Sending... button text wraps to the next line while submitting a review | Done
Bug-847 | Refer & Earn screen API is not integrated | Done
Bug-848 | Wallet amount is not displayed at the top of the Wallet screen (p2p and conversion) | Done
Bug-849 | Current Status card color does not match the design | Done
Bug-850 | Member Status empty-state pie chart does not match the approved design | Done
Bug-851 | Incorrect heading is displayed on the Ambassador Members screen | Done
Bug-852 | Convert USDT to TYX option should be removed from the Conversion screen | Done
Bug-853 | Deposit Request is not working in the Admin panel | Done
Bug-854 | Upload the payment proof text should be removed after uploading the payment proof | Done
Bug-855 | Remove the Payment Proof column from the Deposit Request list | Done
Bug-856 | After updating the TRC20 Address from the Admin panel, the new address appears to be saved. However, after refreshing the page, the old address is displayed again. | Done
Bug-857 | Maximum 8-digit validation is missing for the Request Amount field in Admin | Done
Bug-858 | The TRC20 Transaction Details screen should display the transaction date and time | Done
Bug-859 | On the Admin → Edit TRC20 Address screen, the field label is displayed as "Address 1" instead of "TRC20 Address". | Done
Bug-860 | Start Date and End Date should be removed from TRC20 Transaction Details | Done
Bug-861 | The User ID in the Ambassador module is displayed with the "RBF" prefix instead of the "ID" prefix. | Done
Bug-862 | Display "Senior Ambassador" and "Leader Ambassador" in the Tier Achieved section | Done
Bug-863 | The Transfer Amount initially entered by the user is overwritten when the Admin processes or updates the TRC20 transaction. | Done
Bug-864 | The TRC20 Transaction screen displays an incorrect transaction status. | Done
Bug-865 | Fix the Referral Bonus transaction type and description in Transaction Details. | Done
Bug-866 | When a Referral Bonus is credited to the wallet, the amount is added correctly and the transaction appears in Transaction Details. However, the transaction type and its corresponding type details/description are incorrect. --- app | Done
Bug-867 | QR code download is not working | Done
Bug-868 | Implement shimmer loading on the Service Pack screen | Done
Bug-869 | Remove the notification count badge from the notification icon | Done
Bug-870 | Coming soon --- notification, withdrawals | Done
Bug-871 | Amount separator is missing in pack amount | Done
Bug-872 | Pie chart is not displayed correctly and values are missing | Done
Bug-873 | internet connection... and text and retry button | Done
Bug-874 | Internet connection message is not center-aligned on the KYC screen | Done
Bug-875 | The Order Details screen should support the Pull-to-Refresh functionality to allow users to refresh the latest order information. | Done
Bug-876 | Display cart item count when products are added to the cart | Done
Bug-877 | Positive transaction amounts should display a "+" sign in Transaction Details | Done
Bug-878 | Amount separator is missing in service pack input field | Done
Bug-879 | Amount separator is missing in Transaction and Transaction Details | Done
Bug-880 | Amount separator is missing for Minimum Amount and Your Pack Amount | Done
Bug-881 | Duplicate network connection error messages are displayed --- sign in | Done
Bug-882 | The Request Amount field should be disabled/read-only. | Done
Bug-883 | On the Order Details screen, when the Product dropdown is collapsed, one product should remain visible instead of hiding all products ---- user | Done
Bug-884 | On the Admin → Edit TRC20 Address screen, the Save button should remain disabled until the user makes changes to the TRC20 Address. | Done
Bug-885 | The "Connect Wallet" popup is displayed on the RBF Service Pack screen. As per the current requirement, this popup should be commented out for now. | Done
Bug-886 | The value entered in Transfer Amount should automatically populate the Request Amount field. | Done
Bug-887 | Incorrect transaction type is displayed for USDT transactions | Done
Bug-888 | Remove the notification count badge from the notification icon | Done
Bug-889 | A valid email address in the format a@yopmail.com is being rejected as an invalid email on both the Login and Sign Up screens, | Done
Bug-890 | Pie chart values are not displayed properly | Done
Bug-891 | When a Referral Bonus is credited to the wallet, the amount is added correctly and the transaction appears in Transaction Details. However, the transaction type and its corresponding type details/description are incorrect. --- web | Done
Bug-892 | Implement Referral functionality on the Sign Up screen --- Use web | Done
Bug-893 | The Request Amount and Transfer Amount input fields on the USDT Top-Up (TRC20) screen display incorrect placeholder text --- enter transfer amount, enter requested amount | Done
Bug-894 | When a tier contains only 1 member, the label is displayed as "Members" instead of the singular form. | Done
Bug-895 | Incorrect text is displayed on the Active Members card in the Users module | Done
Bug-896 | The Deposit Requests screen displays incorrect values for Total RBF Supply and Total USDT Received. | Done
Bug-897 | On the Login screen, when a non-existent user attempts to log in, the application displays "Invalid Email and Password" instead of the appropriate message. | Done
Bug-898 | Inactive product should be removed from the cart automatically | Done
Bug-899 | Update the filter on the Reward Logs screen | Done
Bug-900 | Coming soon -- admin -- sub acc, currency supply, moment log, royal flow, withdrawal, fraud | Done
Bug-901 | Copy icon is missing for the TRC20 Address on the USDT Top-Up modal | Done
Bug-902 | Remove the "Closed" status from the Support filter | Done
Bug-903 | Delivery Status and Status colors are inconsistent in Transaction History | Done
Bug-904 | In the Transaction History, the Fee label for P2P transactions displays 0.5% instead of the updated 0.2%. | Done
Bug-905 | Track Order navigates to the Order Details screen instead of the Product Listing screen | Done
Bug-906 | When removing a product from the Cart, there is no loading state while the delete API is in progress. If the user taps the Delete button repeatedly, the product is temporarily removed, reappears, and then gets deleted after the API response. | Done
Bug-907 | On the Email Verification screen, tapping Continue without entering an OTP displays a "Verifying..." state instead of showing a validation error. | Done
Bug-908 | Remove the Notifications module | Done
Bug-909 | Cart item count is not displayed | Done
Bug-910 | If a user signs up but does not complete the OTP verification, attempting to log in with the same account does not redirect the user to the OTP verification screen. | Done
Bug-911 | Search by full name is not working in the Request logs | Done
Bug-912 | Internal Server Error occurs when creating a Deposit Request from the Admin panel. Wallet balance is updated, but the transaction is not recorded in Transaction History after Deposit Request | Done
Bug-913 | Search by full name is not working in the Royal Network | Done
Bug-914 | Search by full name is not working in the Support | Done
Bug-915 | Unverified users are not redirected to the OTP verification screen during login | Done
Bug-916 | Bonus Amount and Network Volume are not displayed on the Admin → User Network Details screen | Done
Bug-917 | Unable to log in | Done
Bug-918 | Time should not be displayed in Pack Transaction History --- Backend | Done
Bug-919 | Incorrect Pack Duration, Start Date, and End Date are displayed in Transaction Details | Done
Bug-920 | The message "You haven't purchased any pack." should be displayed in the Total Weekly Earnings section. (dashboard) | Done
Bug-921 | Incorrect Total RBF Supply and Total USD Receive amounts are displayed on the Admin Deposit Request screen | Done
Bug-922 | Timezone issue (My orders) | Done
Bug-923 | Dashboard should display only two Active Packs | Done
Bug-924 | Weekly Earnings section should be displayed in the Mobile App | Done
Bug-925 | Hide the Active Packs section when no pack has been purchased | Done
Bug-926 | Portfolio should display "0" instead of decimal values when no pack is purchased | Done
Bug-927 | Next Reward In card text should match the Web application | Done
Bug-928 | Time should not be displayed in Pack Transaction History --- App | Done
Bug-929 | A price range slider should be added to the Product Listing screen. The slider and From/To input fields should remain synchronized. | Done
Bug-930 | Search and Filter controls should be hidden when there is no data --- app | Done
Bug-931 | Add a space before the "Read More" / "Read Less" text in KYC Details | Done
Bug-932 | Hide Search and Filter controls while the shimmer loader is displayed | Done
Bug-933 | Timezone issue (All modules / pdf) | Done
Bug-934 | Incorrect PDF title is displayed in RBF Supply Logs export | Done
Bug-935 | Weekly Earnings are credited immediately after purchasing a pack | Done
Bug-936 | Received USDT amount is not displayed until Admin sends RBF | Done
Bug-937 | A hyphen (-) should be displayed properly when the Transfer Amount is empty or unavailable. | Done
Bug-938 | Audit Logs filter size does not match the approved design | Done
Bug-939 | Remove the notification count badge from the notification icon - admin | Done
Bug-940 | Dashboard card layout breaks when Portfolio data is large | Done
Bug-941 | After collapsing the navigation drawer, the dropdown menus are no longer displayed or accessible. | Done
Bug-942 | Remove Transaction ID from the search in request logs. | Done
Bug-943 | The search functionality does not execute while typing in the search bar. It only works after pressing the Enter key ---- Transaction | Done
Bug-944 | Order Management search should be based on Order ID instead of Product Name | Done
Bug-945 | Secure Your Wealth with wraps to the next line on the Admin Sign In screen | Done
Bug-946 | Remove the "Closed" status from the Support filter ----- user | Done
Bug-947 | Unable to increase cart item quantity after refreshing the Dashboard | Done
Bug-948 | Increase TRC20 payment proof upload limit to 5 MB | Done
Bug-949 | Remove dimensions from TRC20 (upload payment proof) | Done
Bug-950 | Internal Server Error occurs when creating a Deposit Request from the Admin panel. Wallet balance is updated, but the transaction is not recorded in Transaction History after Deposit Request | Done
Bug-951 | Gold-Backed RBF Packs wraps to the next line on the Admin Sign In screen | Done
Bug-952 | Gold-Backed RBF Packs text is cut off on the Admin Sign In screen | Done
Bug-953 | Remove the Notifications module --- admin | Done
Bug-954 | Text fields should not accept characters beyond the defined validation limit - review | Done
Bug-955 | Remove Supply Type and Status filters from the Currency Supply Logs screen | Done
Bug-956 | When the "User not found" error is displayed on the Login or Forgot Password screen, it remains visible even after navigating back and reopening the screen. | Done
Bug-957 | Remove "Supply Type" from the Currency Supply Logs search placeholder | Done
Bug-958 | UI shifts after selecting a filter ---- Ambassador Members | Done
Bug-959 | UI shifts after selecting a filter ---- Reward Logs | Done
Bug-960 | Drawer menu icons do not match the approved design | Done
Bug-961 | Withdrawal URL is not configured for the Withdraw button in Wallet | Done
Bug-962 | Total Balance is not showing --- admin panel | Done
Bug-963 | Remove Currency Supply summary cards from the Currency Supply screen | Done
Bug-964 | RBF unit (g) is missing from the Total Balance section | Done
Bug-965 | The Cart badge displays "9+" when the cart contains more than 9 items. The badge should display the exact number of items. | Done
Bug-966 | A price range slider should be added to the Product Listing screen. The slider and From/To input fields should remain synchronized. | Done
Bug-967 | Timezone issue (All modules) | Done
Bug-968 | Admin Dashboard displays incorrect (dummy) values | Done
Bug-969 | RBF value is truncated on the Admin Dashboard | Done
Bug-970 | Display "Document Submitted Successfully" screen after KYC submission | Done
Bug-971 | If a user signs up but does not complete the OTP verification, attempting to log in with the same account does not redirect the user to the OTP verification screen. | Done
Bug-972 | View All Packs navigates to the wrong screen | Done
Bug-973 | Export PDF is not working on the Ambassador module (Admin Panel) | Done
Bug-974 | Export PDF is not working on the Royal Network (Admin Panel) | Done
Bug-975 | Remove the "Good Product" placeholder from the Review Title field -- prestige product | Done
Bug-976 | Include USDT Transfer Amount in the exported PDF | Done
Bug-977 | Unable to delete product (internal server error) | Done
Bug-978 | Increase TRC20 payment proof upload limit to 5 MB | Done
Bug-979 | Implement shimmer loading across the application | Done
Bug-980 | Implement the TRC20 History Details screen | Done
Bug-981 | Add amount separator during conversion -- processing screen | Done
Bug-982 | Remove Time from Gold P2P Transaction Details | Done
Bug-983 | Remove trailing zero after decimal for Gold in P2P Transfer | Done
Bug-984 | Display Product Total Amount in Order Details | Done
Bug-985 | Display Order ID and Order Date on Order Details screen | Done
Bug-986 | Change "Tax" label to "Tax Amount" in Order Details | Done
Bug-987 | Remove TRC20 option from the Wallet three-dot menu | Done
Bug-988 | Wallet screen should load data every time it is opened | Done
Bug-989 | Display Delivery Instruction container with "-" when no instruction is added | Done
Bug-990 | Location icon does not match the approved design in Meeting Place field | Done
Bug-991 | Postal Code should support alphanumeric characters with a 10-character limit | Done
Bug-992 | Set Phone Number field limit to 15 digits | Done
Bug-993 | Country and City dropdowns should match the Web implementation | Done
Bug-994 | Phone number text is displayed incorrectly in Delivery Information | Done
Bug-995 | Incorrect placeholders in Schedule Delivery text fields | Done
Bug-996 | First Name and Last Name fields have no validation | Done
Bug-997 | Dashboard Total Balance is not updated after RBF Convert, TRC20, or P2P transactions | Done
Bug-998 | Remove Time from Buy Gold and Sell Gold Transaction Details | Done
Bug-999 | In the Gold quantity display, when the quantity is greater than 1, the unit should be shown as grams. | Done
Bug-1000 | The application should be restricted to Portrait orientation only. Landscape mode should not be supported. | Done
Bug-1001 | Payment Proof image is not displayed completely | Done
Bug-1002 | In Users → TRC20 Details, the Payment Proof image should maintain a fixed size while the image is loading. | Done
Bug-1003 | In the TRC20 submission flow, the Payment Proof image is not uploaded, but the request is still submitted successfully. | Done
Bug-1004 | The Portfolio and Total Amount displayed on the Dashboard and Header should not include the amount associated with RBF Packs. | Done
Bug-1005 | Add amount separator in Buy/Sell Gold text | Done
Bug-1006 | Remove Start Date and End Date from Buy Gold Transaction Details | Done
Bug-1007 | Time should not be displayed in Pack Transaction History details --- Web | Done
Bug-1008 | Move Phone Number field before Postal Code | Done
Bug-1009 | Postal Code should support alphanumeric characters with a 10-character limit | Done
Bug-1010 | Meeting Type should be optional | Done
Bug-1011 | The field order in the meeting form should be updated according to the design. | Done
Bug-1012 | TRC20 Detail screen does not match the approved design | Done
Bug-1013 | Update button and navigation after submitting TRC20 | Done
Bug-1014 | Insufficient Balance message remains after removing Buy Gold amount | Done
Bug-1015 | Submission Date is not displayed in TRC20 | Done
Bug-1016 | Remove RBF and RBG amounts from the Partner header | Done
Bug-1017 | Display "Insufficient Balance" for Buy/Sell Gold | Done
Bug-1018 | Remove the converted text below the field when balance is insufficient | Done
Bug-1019 | Incorrect placeholder in Buy Gold field | Done
Bug-1020 | Admin Order Management Detail screen does not match the approved design | Done
Bug-1021 | Remove Delivery Status from User Order Details | Done
Bug-1022 | In Deposit Request → Request Details, the Transaction ID should be displayed as a separate field. | Done
Bug-1023 | In Users → TRC20 Details, the Payment Proof image should maintain a fixed size while the image is loading. | Done
Bug-1024 | The First Name and Last Name fields should allow a maximum of 30 characters. | Done
Bug-1025 | Add colon after labels in Delivery Information (order detail) | Done
Bug-1026 | On the user side, the TRC20 Processing screen does not display the transaction amount. | Done
Bug-1027 | The product edit functionality is not working in the Admin and partner product --- gallery url issue | Done
Bug-1028 | Partner products are showing Sales: 0 even when sales data exists. | Done
Bug-1029 | In the Wallet Transaction filters, options for RBF and Gold should be available. (backend s hogaya h screen blank horhi h dekhlena ahmed ko bhi boldena ) | Done
Bug-1030 | In the Transaction filters, options for RBF and Gold should be available. (backend s hogaya h screen blank horhi h dekhlena ahmed ko bhi boldena) | Done
Bug-1031 | Remove trailing zero from Deposit amount | Done
Bug-1032 | Display RBF as the transaction type for Buy Gold | Done
Bug-1033 | Remove Wallet filter from Transactions | Done
Bug-1034 | Order placed notification missing --- user | Done
Bug-1035 | Duplicate "g" unit is displayed for the RBG amount in Admin Total Balance | Done
Bug-1036 | When increasing or decreasing the quantity of a product in the Cart, the "Adding" loading state is incorrectly displayed on another product instead of only the product being updated. | Done
Bug-1037 | Duplicate QR codes are displayed in the Mobile Responsive view | Done
Bug-1038 | OTP is received twice on the Login screen | Done
Bug-1039 | Move the Referral Code field above the Password field | Done
Bug-1040 | Back button is not working on the Email Validation screen | Done
Bug-1041 | Product Images Not Displayed | Done
Bug-1042 | Hide Empty Categories from Product Filter | Done
Bug-1043 | The Equivalent symbol is not displayed in the Cart. | Done
Bug-1044 | The Equivalent USDT value is not displayed on the Product Details screen. | Done
Bug-1045 | Replace Dollar Symbol with USDT in Product Listing | Done
Bug-1046 | In the Marketplace Transaction Details, the “Paid From:” label should be displayed. | Done
Bug-1047 | Whenever the user navigates to Partner Products, the product listing should refresh automatically. This should also apply when the user navigates back from the Product Details screen. | Done
Bug-1048 | Add shimmer --- partner all products | Done
Bug-1049 | Partner Picture Not Displayed (product details) | Done
Bug-1050 | In the Marketplace Transactions, the colors used for the Delivery Status need to be updated. | Done
Bug-1051 | When a user adds Delivery Instructions and the Admin declines the order, the Delivery Instructions field in Order Management details is replaced by the Rejection Reason. | Done
Bug-1052 | After an order is placed successfully, when the user clicks “Go to Marketplace”, the Marketplace page does not refresh. | Done
Bug-1053 | The “Rows per page:” text is moving when the table slider is moved --- Admin and partner | Done
Bug-1054 | Marketplace Delivery Status is not updated in Transactions | Done
Bug-1055 | In the Transaction section, the Wallet filter should also include a USDT option. | Done
Bug-1056 | Reverse Transaction When Order Is Rejected | Done
Bug-1057 | Incorrect currency unit displayed in Marketplace Transaction Unit Price (currently:USDT) | Done
Bug-1058 | The amount displayed in the Marketplace Transaction does not match the amount shown in the corresponding Order Details. The decimal value after the point is missing from the transaction amount. | Done
Bug-1059 | Add RBF and USDT filters in Order Management | Done
Bug-1060 | Incorrect Rating displayed on Web | Done
Bug-1061 | Add Order Type Filter from My Orders | Done
Bug-1062 | Remove Date from Marketplace Transactions Details | Done
Bug-1063 | Incorrect currency unit displayed in Marketplace Transaction Unit Price (currently:RBG) | Done
Bug-1064 | When an admin rejects an order, the “Contact Support” text is displayed on the user's Order Details screen. Remove this text | Done
Bug-1065 | Complete Delivery Information is not displayed in Order Details | Done
Bug-1066 | Business Name should start with a capital letter (Examples: Test122, Test122 Products) --- all products (partner) | Done
Bug-1067 | Display trailing zero in Product Rating (Example: 5.0 instead of 5) | Done
Bug-1068 | Sign in screen appears when paying with card | Done
Bug-1069 | Separate Orders for Products with Different Payment Links (cart) | Done
Bug-1070 | Pay with Card button is positioned too low | Done
Bug-1071 | Error Occurs When Paying with Card / sign in appears when paying with card | Done
Bug-1072 | In My Orders on the web, the Delivery Information section does not match the design and layout used in the mobile app. | Done
Bug-1073 | Cart Does Not Clear After Order Placement | Done
Bug-1074 | USDT Equivalent Not Displayed in RBF Marketplace (minh y tmhri trf s hoga nh smjh ae tw mujh s pochlena) | Done
Bug-1075 | Replace Order Type Filter from My Orders | Done
Bug-1076 | Separate Orders for Products with Different Payment Links (cart) | Done
Bug-1077 | Sign In Screen Appears After Returning from Order Details | Done
Bug-1078 | Remove USD Price Filter from Product Listing | Done
Bug-1079 | RBF Shop Does Not Update Without Refresh | Done
Bug-1080 | Back to Prestige Button Visible After Successful Order | Done
Bug-1081 | Product Category Name Not Fully Displayed in Order Details | Done
Bug-1082 | Transaction Status Shows Pending After Successful Order | Done
Bug-1083 | USDT Amount Not Displayed in Partner Product Order Management | Done
Bug-1084 | Prestige Type Displayed for RBF Product (source) | Done
Bug-1085 | Conversion filter is not working properly (Transaction type) | Done
Bug-1086 | Partner Product prices should be in RBF only. | Done
Bug-1087 | Applicable tax amounts should also be shown and calculated in RBF. | Done